## RA
Risk-Based Hazard Analysis | [8 empty] | Security Assessment
Commuter Rail Project Only | [8 empty] | All Projects
MassDOT/MBTA Railroad System Safety Program Plan (2022)
| Frequent (A) | Probable (B) | Occasional (C) | Remote (D) | Improbable (E) | [5 empty] | (I) | (II) | (III) | (IV)
Catastrophic (5) | 5A | 5B | 5C | 5D | 5E | [5 empty] | Catastrophic | Critical | Marginal | Negligible
Severe (4) | 4A | 4B | 4C | 4D | 4E |  |  |  | Frequent | A | IA | IIA | IIIA | IVA
Serious (3) | 3A | 3B | 3C | 3D | 3E |  |  |  | Probably | B | IB | IIB | IIIB | IVB
Moderate (2) | 2A | 2B | 2C | 2D | 2E |  |  |  | Occasional | C | 1C | IIC | IIIC | IVC
Minor (1) | 1A | 1B | 1C | 1D | 1E |  |  |  | Remote | D | 1D | IID | IIID | IVD
[9 empty] | Improbable | E | 1E | IIE | IIIE | IVE
Security Assessment Determination | [8 empty] | Security Assessment Determination
Risk Score | Operational Authority |  |  | Review |  |  |  |  | Rating | Index |  | Description
Very High | Accountable Manager (General Manager) |  |  | Safety department |  |  |  |  | High | IA, IB, IC, IIA, IIB |  | Unacceptable; threat must be mitigated
High | Vice President |  |  | Safety department
Medium | Director (equivalent) |  |  | Safety department |  |  |  |  | Serious | ID, IE, IIC, IIIA, IIIB, IVA |  | Undesirable, with Management Decisions; threat should be mitigated, if possible, and within financial constraints.
Low | Manager |  |  | Not required
[9 empty] | Low | IID, IIE, IIIC, IIID, IIIE, IVB, IVC, IVD, IVE |  | Acceptable with Management Review; no additional countermeasures are currently required.
Likelihood Table
| Frequency |  |  |  | % Likelihood
Frequent (A) | Once per week |  |  |  | >90% |  |  |  | Threat Severity Categories
Probable (B) | Likely to occur multiple times in a month |  |  |  | 70%-89% |  |  |  | Severity |  | Characteristics
Occasional (C) | likely to occur at least once or multiple times in a year |  |  |  | 40%-69% |  |  |  | Catastrophic | I | Loss of life and/or extensive damage requiring months to repair; long-term interruption.
Remote (D) | Likely to occur multiple times in 1-5 years |  |  |  | 10%-39%
Improbable (E) | Never - Once every 5 eyars |  |  |  | <10% |  |  |  | Critical | II | Serious injuries and/or significant damage requiring weeks to repair; long-term interruption.
Severity Table | [8 empty] | Marginal | III | Minor injuries and/or minor damage (requiring seven or fewer days to repair); short-term interruption.
| A - Financial Impact | B - Equip. / Infr. Damage | C - Health & Safety | D - Service Disruption | E - Brand & Reputation | F - Environment & Community | G - Projects (Scope/Sch.) | H - Projects (Budget)
[9 empty] | Negligible | IV | No injury and/or no minor property damage; little or no interruption.
Catastrophic (5) | Enterprise: >$10m or Dept. Budget: >30% | a. Leads to write-off to loco or coach b. Equipment is unrecoverable and written off. | Multiple fatalities | Cancellation of 9 or more trains | a. Total loss of shareholder support. b. MBTA Operating Agreement termination. c. Regulatory action that threatens ability to operate network. | a. Irreversible damage to the environment including habitat and species. B. Community impacted for >12 months by KCS related activity. | Scope impact is complete requiring a total rework of the project. Schedule impact >50% increase to total schedule length | >$2m
Threat Severity Categories
[9 empty] | Description | Level | Specific Event
[9 empty] | Frequent | A | Indicates that a definite threat exists against the asset and that an adversary has both the capability and intent to attack or commit a criminal act, asset is targeted on a frequently recurring basis.
[9 empty] | Probable | B | Indicates that a credible threat exists against the asset based on knowledge of an adversary’s capability and intent to attack or commit a criminal act against the asset, based on related incidents having taken place at similar assets or in similar situations.
Severe (4) | Enterprise: $5m- $10m or Dept. Budget: 15-30% | a. Major damage to system or multiple components. b. Requires extensive repairs greater than 3 months out of service (i.e., HEP fires. | a. Single fatality and/or permanent life altering disability. b. Moderate or reversible disability or impairment to one or more persons. | Cancellation of up to 8 trains | a. Formal non-safety related public criticisim of the operation. b. Negative national press. c. Sr. Exec. Leave involuntarily. d. Major enforcement action from a regulator. e. Coordinated adverse union action that impacts service. f. "Bad Actor" crime, violation, leaking info, cyberattack g. Threatens MBTA confidence to send us supplemental work. | a. Community impacted for 6-12 months by KCS related activities. b. Significant impacts to the environment e.g., 700-gal spill. c. Multiyear redmedial action greater than 3 years. | Scope impact is significant requiring substantial adjustment to design, and/or the (re)purchase of long lead material to complete the work. Schedulle impact 40%-50% increase to total schedule length | $1m - $2m | Occasional | C | Indicates that there is a possible threat to the asset based on an adversary’s desire to compromise similar assets
[9 empty] | Remote | D | Indicates that there is a low threat against the asset and that few known adversaries would pose a threat to the asset.
[9 empty] | Improbable | E | Indicates no credible evidence of capability or intent and no history of actual or planned threats against the asset.
[9 empty] | Eliminated | F | Indicates threat has been eliminated.
Serious (3) | Enterprise: $1m- $5m or Dept. Budget: 5-<15% | a. Single component failure. b. 1-3 months out of service (e.g., 1219 damage to windshield) | a. Hospitalization required b. Medium term largely reversible disabilityto one or more persons. c. Lost time injury | a. 31-60 min delay, and/or b. Impacts to 8 trains and/or c. Results in a cancellation | a. FRA Violation b. Formal T Compliant c. Criticism from T GM or Board | Reversible damage through remediation (1-3 years). | Scope impact will increase design changes, and/or the change or addition of new material to complete the scope. Schedule Impact 25%-40% increase to total schedule length. | $250,000 - $1m
Moderate (2) | Enterprise: $125k-$1m or Dept. Budget: 0.5-<5% | a. 1 week to 1 month out of service, e.g., railings on 1135 | Reversible disability requiring hospital treatment | a. 21-30 min delay, and/or b. Impacts 4 trains | a. Informal MBTA Complaint b. Escalation to KCS leadership c. Abutter or passenger complaints esc. to elected official d. Negative local reporting | Impacts to environment with less than 1 year remediation. | Scope impact will require some adjustments to design and material requirements will shorten. Schedule impact 15%-25% increase to total schedule. | $50,000 - $250,000
Minor (1) | Enterprise: $0- $125k or Dept. Budget: <0.5% | a. Less than 1 week out of service, e.g., grab rail or head light | First aid only. | a. Up to 20 min delay, and/or b. Impacts a max of 3 trains | a. Emp. Diciplined b. Passengers are aware and affected. | No remedial requirement, temporary impact on evnironment | Scope impact is minor requiring no changes to design. Schedule impact 0%-15% increase to total schedule. | $0 - $50,000

## MOV
Means of Verification
All Projects
Design, Construction, and Testing Phases
Design
DS | Design Submittal
CO | Change Order
CA | Calculations
O | Other
Construction
CS | Construction Submittal (e.g., Shop Drawings, Material Data, Calculations, etc.)
TS | Test Submittal
M | Measurement(s)
VI | Visual Inspection
C | Certifications
O | Other
Testing
TS | Test Submittal (e.g., Procedures, Results, etc.)
M | Measurement
VI | Visual Inspection
O | Other

## CEL
Certifiable Elements List (CEL) Safety and Security Certification Worksheet
Project Name: [Enter Project Name]
Contract Number: [Enter Contract Number]
Certifiable Element: [Enter Certifiable Element 1...]
[Enter Sub-Element 1]
[Enter Sub-Element 2]
[Enter Sub-Element 3]
Certifiable Element: [Enter Certifiable Element 2...]
[Enter Sub-Element 1]
[Enter Sub-Element 2]
[Enter Sub-Element 3]
Certifiable Element: [Enter Certifiable Element 3...]
[Enter Sub-Element 1]
[Enter Sub-Element 2]
[Enter Sub-Element 3]

## RBHA
Risk-Based Hazard Analysis FRA-Specific Safety and Security Certification Worksheet
Project Name: [Enter Project Name] | [5 empty] | Design Consultant(s) |  | Contractor(s) |  | SMWG Approval Date |  | SMRC Approval Date | Rev. No. | Rev Date | Document Status
Contract Number: [Enter Contract Number] | [5 empty] | [Enter Company Name(s)] |  | [Enter Company Name(s)] |  | [Enter Date] |  | [Enter Date] | [Add No.] | [Add Date] | DRAFT
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
PHA No. | Hazard Description |  |  |  | Initial Risk Rating (Pre-Resolution) |  |  | Proposed Mitigation | Residual Risk Rating (Post-Resolution) |  |  | Implemented Mitigation | Final Hazard Status
| Sub-Element | Hazard | Potential Cause(s) | Effect(s) | Severity (5 to 1) | Probability (A-E) | Risk Index |  | Severity (5 to 1) | Probability (A-E) | Risk Index |  | Status (Open/Closed) | Safety Verification | Date Closed | Comments
Certifiable Element: [Enter Certifiable Element 1...]
Open
Open
Open
Certifiable Element: [Enter Certifiable Element 2...]
Open
Open
Open
Certifiable Element: [Enter Certifiable Element 3...]
Open
Open
Open
Certifiable Element: [Enter Certifiable Element 4...]
Open
Open
Open

## SEC
Security Assessment Safety and Security Certification Worksheet
Project Name: [Enter Project Name] | [5 empty] | Design Consultant(s) |  | Contractor(s) |  | SMWG Approval Date |  | SMRC Approval Date | Rev. No. | Rev Date | Document Status
Contract Number: [Enter Contract Number] | [5 empty] | [Enter Company Name(s)] |  | [Enter Company Name(s)] |  | [Enter Date] |  | [Enter Date] | [Add No.] | [Add Date] | DRAFT
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
SA No. | Hazard Description |  |  |  | Initial Risk Rating (Pre-Resolution) |  |  | Proposed Mitigation | Residual Risk Rating (Post-Resolution) |  |  | Implemented Mitigation | Final Hazard Status
| Sub-System | Vulnerability | Potential Cause(s) | Effect(s) | Severity (1-4) | Probability (A-E) | Safety Risk Index |  | Severity (1-4) | Probability (A-E) | Safety Risk Index |  | Status (Open/Closed) | Safety Verification | Date Closed | Comments
Certifiable Element: [Enter Certifiable Element 1...]
Open
Open
Open
Certifiable Element: [Enter Certifiable Element 2...]
Open
Open
Open
Certifiable Element: [Enter Certifiable Element 3...]
Open
Open
Open
Certifiable Element: [Enter Certifiable Element 4...]
Open
Open
Open

## CIL
Certifiable Items List (CIL) Safety and Security Certification Worksheet
Project Name: [Enter Project Name] | [15 empty] | Design Consultant(s) |  |  | Contractor(s) |  |  | SMWG Approval Date |  | SMRC Approval Date |  | Rev. No. | Rev Date | Document Status
Contract Number: [Enter Contract Number] | [15 empty] | [Enter Company Name(s)] |  |  | [Enter Company Name(s)] |  |  | [Enter Date] |  | [Enter Date] |  | [Add No.] | [Add Date] | DRAFT
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
LEVEL 1: Element | LEVEL 2: Sub-Element | LEVEL 3: Item | LEVEL 4: Requirement | PHA No. | SA No. | SCIL (Yes/No) | Requirement (description from the source) | Source (e.g., standards, design directives / guidelines, codes, etc.) | Design Criteria Conformance Checklist (DCCC) | [6 empty] | Construction Specification Conformance Checklist (CSCC) | [5 empty] | Testing Specification Conformance Checklist (TVCC) | [5 empty] | Comments / Notes
[9 empty] | Means of Verification (ref. to "MOV" tab) | Drawing Page Reference (if applicable) | Design Consultant |  | MBTA Safety |  |  | Means of Verification (ref. to "MOV" tab) | Contractor |  | MBTA Safety |  |  | Means of Verification (ref. to "MOV" tab) | Contractor |  | MBTA Safety
[11 empty] | Initials | Date | Initials | Date | Status |  | Initials | Date | Initials | Date | Status |  | Initials | Date | Initials | Date | Status
1
1 | 1
1 | 1 | 1
1 | 1 | 1 | 1 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
1 | 1 | 1 | 2 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
1 | 1 | 1 | 3 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
1 | 1 | 1 | 4 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
1 | 2
1 | 2 | 1
1 | 2 | 1 | 1 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
1 | 2 | 1 | 2 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
1 | 2 | 1 | 3 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
1 | 2 | 1 | 4 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
2
2 | 1
2 | 1 | 1
2 | 1 | 1 | 1 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
2 | 1 | 1 | 2 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
2 | 1 | 1 | 3 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
2 | 1 | 1 | 4 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
2 | 2
2 | 2 | 1
2 | 2 | 1 | 1 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
2 | 2 | 1 | 2 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
2 | 2 | 1 | 3 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open
2 | 2 | 1 | 4 | [11 empty] | Open | [5 empty] | Open | [5 empty] | Open

## OHA
Operational Hazard Analysis (OHA) Safety and Security Certification Worksheet
Project Name: [Enter Project Name] | [5 empty] | Design Consultant(s) |  | Contractor(s) |  | SMWG Approval Date |  | SMRC Approval Date | Rev. No. | Rev Date | Document Status
Contract Number: [Enter Contract Number] | [5 empty] | [Enter Company Name(s)] |  | [Enter Company Name(s)] |  | [Enter Date] |  | [Enter Date] | [Add No.] | [Add Date] | DRAFT
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
OHA No. | Hazard Description |  |  |  | Initial Risk Rating (Pre-Resolution) |  |  | Proposed Mitigation | Residual Risk Rating (Post-Resolution) |  |  | Implemented Mitigation | Final Hazard Status
| Sub-System | Hazard | Potential Cause(s) | Effect(s) | Severity (5 to 1) | Probability (A-E) | Risk Index |  | Severity (5 to 1) | Probability (A-E) | Risk Index |  | Status (Open/Closed) | Safety Verification | Date Closed | Comments
Certifiable Element: [Enter Certifiable Element 1...]
Open
Open
Open
Certifiable Element: [Enter Certifiable Element 2...]
Open
Open
Open
Certifiable Element: [Enter Certifiable Element 3...]
Open
Open
Open

## HTL
Hazard Tracking Log (HTL) Safety and Security Certification Worksheet
Project Name: [Enter Project Name] | [7 empty] | Design Consultant(s) |  | Contractor(s) |  | SMWG Approval Date |  | SMRC Approval Date | Rev. No. | Rev Date | Document Status
Contract Number: [Enter Contract Number] | [7 empty] | [Enter Company Name(s)] |  | [Enter Company Name(s)] |  | [Enter Date] |  | [Enter Date] | [Add No.] | [Add Date] | DRAFT
HTL No. | Hazard Source | Source No. | Hazard Description |  |  |  | Initial Risk Rating (Pre-Resolution) |  |  | Proposed Mitigation | Residual Risk Rating (Post-Resolution) |  |  | Implemented Mitigation | Final Hazard Status
|  |  | Element | Hazard | Potential Cause(s) | Effect(s) | Severity (5 to 1) | Probability (A-E) | Risk Index |  | Severity (5 to 1) | Probability (A-E) | Risk Index |  | Status (Open/Closed) | Safety Verification | Date Closed | Comments
HTL-## | PHA | PHA-01 | [12 empty] | Open |  |  |  | FMEA
[15 empty] | Open |  |  |  | FTA
[15 empty] | Open |  |  |  | OHA
[15 empty] | Open |  |  |  | Other
[15 empty] | Open |  |  |  | PHA
[15 empty] | Open |  |  |  | SA
[15 empty] | Open |  |  |  | Software HA
[15 empty] | Open |  |  |  | Sub-System HA
[15 empty] | Open |  |  |  | System HA
Open
Open
Open

## ORCC
Operational Readiness Conformance Checklist (ORCC) Safety and Security Certification Worksheet
Project Name: [Enter Project Name] | [6 empty] | Design Consultant(s) | Contractor(s) |  |  | SMWG Approval Date |  | Rev. No. | Rev Date | Document Status
Contract Number: [Enter Contract Number] | [6 empty] | [Enter Company Name(s)] | [Enter Company Name(s)] |  |  | [Enter Date] |  | [Add No.] | [Add Date] | DRAFT
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
ORCC No. | Operational Requirements | [6 empty] | Means of Verification | Date Approved | Ownership | Verification
| Function or Project Component | Certifiable Sub-Element | Hazard Source | Source No. | SA No. | Reference | Title or Description |  |  |  | Project Verification | Safety Verification | Status (Open/Closed) | Date Closed | Comments
Certifiable Element: [Enter Certifiable Element 1...]
Open
Open
Open
Certifiable Element: [Enter Certifiable Element 2...]
Open
Open
Open
Certifiable Element: [Enter Certifiable Element 3...]
Open
Open
Open