## Slide 1
MBTA Sullivan Square Station
Lower Busway & Parking Lot Reconstruction
Public Meeting
April 5, 2018

## Slide 2
Project Proponent: Wynn Development
Developer/Funding: Wynn Development
Contractor: D.W. White Construction
Designers: AECOM/Howard Stein Hudson
Construction Cost: $4.5M
Start Date: April, 2018
Completion Date: October, 2018
MBTA Sullivan Square Station
Lower Busway & Parking Lot Reconstruction

## Slide 3
MAIN STREET (MYSTIC AVE)
MAFFA WAY (BROADWAY)
CAMBRIDGE STREET
BEACHAM STREET
RUTHERFORD AVE
D STREET
SPICE STREET
RUTHERFORD AVE
ALFORD STREET
INTERSTATE 93
I-93 N OFFRAMP
NORTH TO EVERETT
SOUTH TO BOSTON
WEST TO SOMERVILLE
WEST TO CAMBRIDGE
MAIN STREET
Project Location

## Slide 4
MAIN STREET (MYSTIC AVE)
CAMBRIDGE STREET
BEACHAM STREET
RUTHERFORD AVE
D STREET
SPICE STREET
RUTHERFORD AVE
ALFORD STREET
INTERSTATE 93
I-93 N OFFRAMP
NORTH TO EVERETT
SOUTH TO BOSTON
WEST TO SOMERVILLE
WEST TO CAMBRIDGE
MAIN STREET
MAFFA WAY (BROADWAY)
Project Location

## Slide 5
Existing Operations
SPICE STREET
I-93 N
OFFRAMP
BEACHAM STREET
MAIN STREET
MBTA BUS ONLY AREA
MBTA LOWER BUSWAY
MBTA UPPER BUSWAY
(BELOW INTERSTATE 93)
MAFFA WAY
MBTA PARKING LOT
CITY OF BOSTON PARKING LOTS
MAFFA WAY
CAMBRIDGE STREET
Station Facts
Parking capacity of 222 spaces.
130% daily utilization rate.
Nearly 8,000 bus boardings each weekday (5th busiest bus station).
Over 600 buses for 12 routes serve Sullivan each weekday.
Between 2009 and 2012, ridership on local bus routes increased by 20%.

## Slide 6
Existing Operations – Parking Services
SPICE STREET
I-93 N
OFFRAMP
BEACHAM STREET
MAIN STREET
MAFFA WAY
MBTA BUS ONLY AREA
MAFFA WAY
MBTA PARKING LOT
CITY OF BOSTON PARKING LOTS
P
CAMBRIDGE STREET
MBTA LOWER BUSWAY
MBTA UPPER BUSWAY
(BELOW INTERSTATE 93)
PARKING MOVEMENTS
P
P
Station Facts
Parking capacity of 222 spaces.
130% daily utilization rate.
Nearly 8,000 bus boardings each weekday (5th busiest bus station).
Over 600 buses for 12 routes serve Sullivan each weekday.
Between 2009 and 2012, ridership on local bus routes increased by 20%.

## Slide 7
Existing Operations – Bus Operations
SPICE STREET
I-93 N
OFFRAMP
CAMBRIDGE STREET
BEACHAM STREET
MAIN STREET
MAFFA WAY
MBTA BUS ONLY AREA
MBTA LOWER BUSWAY
MBTA UPPER BUSWAY
(BELOW INTERSTATE 93)
MAFFA WAY
MBTA PARKING LOT
CITY OF BOSTON PARKING LOTS
B
B
B
B
B
BUS MOVEMENTS
B
B
Station Facts
Parking capacity of 222 spaces.
130% daily utilization rate.
Nearly 8,000 bus boardings each weekday (5th busiest bus station).
Over 600 buses for 12 routes serve Sullivan each weekday.
Between 2009 and 2012, ridership on local bus routes increased by 20%.

## Slide 8
Existing Operations – Parking Services and Bus Operations
Station Facts
Parking capacity of 222 spaces.
130% daily utilization rate.
Nearly 8,000 bus boardings each weekday (5th busiest bus station).
Over 600 buses for 12 routes serve Sullivan each weekday.
Between 2009 and 2012, ridership on local bus routes increased by 20%.
SPICE STREET
I-93 N
OFFRAMP
CAMBRIDGE STREET
BEACHAM STREET
MAIN STREET
MAFFA WAY
MBTA BUS ONLY AREA
MBTA LOWER BUSWAY
MBTA UPPER BUSWAY
(BELOW INTERSTATE 93)
MAFFA WAY
MBTA PARKING LOT
CITY OF BOSTON PARKING LOTS
P
P
B
B
B
B
B
PARKING MOVEMENTS
P
BUS MOVEMENTS
B
B

## Slide 9
Operational Features:
New public right-of-way between Cambridge Street and Maffa Way.
Separation of Parking Lot and Busways.
197 Parking Spaces.
Relocated bus Layover Area.
New additional Lower Busway.
4 newly signalized intersections.
New bus only entrance via Main Street.
New Upper Busway exit to Cambridge Street.
Infrastructure Improvements:
New bus shelters
New lighting system.
New drainage system.
New security infrastructure.
New pavement and striping.
New traffic and wayfinding signage.
Proposed Design

## Slide 10
Bus Service:
All 12 MBTA bus routes serving Sullivan Square Station will remain fully operational during construction.
A phased construction effort will require temporary closures of busways.
Temporary wayfinding signage will be posted throughout construction.
Parking Service:
Parking payment method has been transitioned to pay-by phone.
Capacity during construction will be reduced including periods of full closure.
Lot entry and exit will be relocated during construction.
Alternative MBTA parking is available at the MBTA’s Station Landing Garage (80 Station Landing, Medford).
  Station Landing Garage contains pedestrian bridge access to MBTA Wellington Station.
Parking lot detour signage will be posted throughout construction.
Orange Line Service:
No changes to service due to construction.
Sullivan Square Station will remain accessible throughout construction.
Service During Construction

## Slide 11
Construction – Phase 1 – 2 weeks (April 19 – May 3)
P
CONSTRUCTION AREA
CAMBRIDGE STREET
MAIN STREET
MAFFA WAY
Activities:
Remove median in busway
Realign busway
Construct temp busway
MBTA Service:
Parking reduced by 40%
  222 to 134 spaces
Relocated parking lot entry
Relocated pick-up/drop-off
No change to bus service
No change to station access
P
MAFFA WAY

## Slide 12
Construction – Phase 2 – 10 weeks (May 4 – July 13)
Activities:
Re-alight retaining wall between the upper and lower busways
Reconstruct lower busway
MBTA Service:
Parking reduced by 40%
  222 to 134 spaces
Relocated parking lot entry
Relocated pick-up/drop-off
Lower busway service relocated to temp busway. (routes 86, 91, 92 inbound, 93, and CT2)
No change to station access
MAIN STREET
CAMBRIDGE STREET
P
P
CONSTRUCTION AREA
CONSTRUCTION AREA
MAFFA WAY
TEMPORARY LOWER BUSWAY
UPPER BUSWAY

## Slide 13
Construction – Phase 2a – 2 weekends (6/30-7/1 & 7/7-7/8)
Activities:
Re-grade busway along Cambridge Street
MBTA Service:
Parking lot closed.
Relocated pick-up/drop-off
Lower busway service relocated to temp busway (routes 86, 91, 92 inbound, 93, and CT2).
Upper busway service relocated to new Lower Busway 1 (routes 89, 90, 92 outbound, 95, 101, 104, 105, 109).
Station access from Cambridge Street west detoured.
MAIN STREET
CAMBRIDGE STREET
CONSTRUCTION AREA
MAFFA WAY
MAFFA WAY
LOWER BUSWAY 2
LOWER BUSWAY 1

## Slide 14
Construction – Phase 3 – 10 weeks (July 14 – September 22)
Activities:
Reconstruct parking lot perimeter
MBTA Service:
Parking reduced by 60%
  222 to 88 spaces
Relocated parking lot entry and exit
Pick-up/drop-off area re-opened.
Lower busway service relocated to Lower Busway 1 (routes 86, 91, 92 inbound, 93, and CT2).
Upper Busway Service Restored (routes 89, 90, 92 outbound, 95, 101, 104, 105, 109).
CONSTRUCTION AREA
CONSTRUCTION AREA
P
P
MAIN STREET
MAFFA WAY
CAMBRIDGE STREET
MAFFA WAY
LOWER BUSWAY 1
UPPER BUSWAY

## Slide 15
Construction – Phase 4 – 4 weeks (September 23 – October 21)
Activities:
Reconstruct parking lot interior
Regrade Upper Busway entry and exit
MBTA Service:
Parking lot closed
Lower busway service relocated to Lower Busway 2 (routes 86, 91, 92 inbound, 93, and CT2).
Upper Busway Service relocated to Lower Busway 1 (routes 89, 90, 92 outbound, 95, 101, 104, 105, 109).
Station access detoured from Maffa Way and Cambridge Street west
MAIN STREET
CONSTRUCTION ARA
MAFFA WAY
CAMBRIDGE STREET
CONSTRUCTION AREA
CONSTRUCTION AREA
MAFFA WAY
LOWER BUSWAY 2
LOWER BUSWAY 1

## Slide 16
Construction – Final Condition
Activities:
Work complete
MBTA Service:
Parking lot re-opened with 197 spaces available.
Parking lot accessed via Beacham Street
All 3 busways operational with some bus berth relocations.
  Routes 89, 91, and CT2 relocated to Upper Busway
  Routes 104, 105, 109 relocated to Lower Busway 1
  Routes, 90, 92, and 93 relocated to Lower Busway 2
MAIN STREET
MAFFA WAY
CAMBRIDGE STREET
MAFFA WAY
BEACHAM STREET
LOWER BUSWAY 1
UPPER BUSWAY
P
LOWER BUSWAY 2
BEACHAM STREET

## Slide 17
Public Communications Strategy
MBTA Flyer Drops
  Prior to and during Construction
MBTA Alerts
  Text Message Alerts
  Email Alerts
MBTA Website
  Project Specific Site is Currently Active (https://www.mbta.com/projects/sullivan-square-lower-busway-and-parking-lot-reconstruction
Informational Graphic Displays on Site

## Slide 18
QUESTIONS?
or send questions to: sullivanquestions@mbta.com